## Risk Register
Risk ID | Asset | Asset Type | Risk Statement | Threat | Vulnerability | Existing Controls | CIA Impact | Likelihood | Impact | Inherent Risk Score | Inherent Risk Level | Treatment | Additional Controls | Residual Likelihood | Residual Impact | Residual Risk Score | Residual Risk Level | Owner | Status
R-001 | Proxmox Virtualisation Host | Infrastructure | Unpatched vulnerabilities on the Proxmox host could be exploited by an attacker, resulting in unauthorised access to virtual machines and disruption of multiple services. | Exploitation of known vulnerability | Delayed security patching | Administrative access restricted to LAN; firewall rules; strong administrator credentials | High – Integrity / Availability | 3 | 5 | 15 | Critical | Mitigate | Formal patch-management schedule; restrict management access; maintain configuration backups | 2 | 5 | 10 | High | Infrastructure Manager | Open
R-002 | OPNsense Firewall | Network Security | Misconfigured firewall rules could permit unauthorised network traffic, allowing an attacker to access systems that should be isolated. | Unauthorised network access | Firewall misconfiguration | OPNsense firewall; network segmentation; default-deny approach where appropriate | High – Confidentiality / Integrity | 3 | 5 | 15 | Critical | Mitigate | Periodic firewall-rule review; documented rule purpose; remove unused rules | 2 | 5 | 10 | High | Network Manager | Open
R-003 | Windows 11 Workstation | Endpoint | Malware infection on the Windows 11 workstation could compromise credentials or data and provide a foothold for further attacks. | Malware / phishing | Endpoint compromise | Windows security features; firewall; restricted network environment | High – Confidentiality / Integrity | 3 | 4 | 12 | High | Mitigate | Keep OS and applications patched; endpoint protection; least privilege; user awareness | 2 | 4 | 8 | Medium | Endpoint Manager | Open
R-004 | Ubuntu File Server | Server | Unauthorised access to the Ubuntu file server could expose, alter or delete stored information. | Unauthorised access | Inadequate file permissions or authentication | Linux permissions; firewall; restricted network access | High – Confidentiality / Integrity / Availability | 3 | 4 | 12 | High | Mitigate | Least-privilege permissions; separate user accounts; SSH hardening; regular backup and restore testing | 2 | 4 | 8 | Medium | System Owner | Open
R-005 | Network Configuration Data | Information | Loss or unauthorised modification of firewall and network configuration backups could prevent timely recovery following a system failure. | Data loss / system failure | Insufficient configuration backup | Manual configuration records | High – Availability / Integrity | 3 | 4 | 12 | High | Mitigate | Automated or scheduled encrypted backups; offline copy; periodic restoration test | 2 | 4 | 8 | Medium | Network Manager | Open
R-006 | Kali Linux Security Testing VM | Virtual Machine | A compromised or misconfigured security-testing VM could be used to attack other systems or bypass intended network boundaries. | Compromised testing environment | High-risk security tools and broad network access | Isolated lab environment; VLAN segmentation | Medium – Integrity / Availability | 2 | 4 | 8 | Medium | Mitigate | Restrict network routes; shut down when not required; snapshot before testing; document authorised test scope | 1 | 4 | 4 | Low | Security Manager | Open
R-007 | OPNsense / Network Management Interface | Management Interface | Compromise of an administrator account could allow an attacker to alter firewall or network settings and compromise connected systems. | Credential compromise | Single-factor administrator authentication | Management interface not exposed directly to the internet | Critical – Integrity / Availability | 3 | 5 | 15 | Critical | Mitigate | MFA where supported; unique administrator accounts; disable unused accounts; strong password policy | 2 | 5 | 10 | High | Security Manager | Open
R-008 | Virtual Machine Backups / Snapshots | Backup | Failure to maintain reliable backups could result in permanent loss of systems or data following hardware failure, ransomware or configuration error. | Hardware failure / ransomware / human error | Insufficient or untested backups | VM snapshots where used | High – Availability | 3 | 5 | 15 | Critical | Mitigate | 3-2-1 backup approach; offline or separate backup copy; scheduled restore testing | 2 | 5 | 10 | High | Infrastructure Manager | Open
R-009 | VLAN 30 Playground Network | Network | Insufficient isolation of the playground VLAN could allow a compromised test system to access trusted network resources. | Lateral movement | Inadequate inter-VLAN restrictions | VLAN segmentation; OPNsense firewall rules | High – Confidentiality / Integrity | 2 | 5 | 10 | High | Mitigate | Explicit deny rules between playground and trusted networks; periodic segmentation testing | 1 | 5 | 5 | Medium | Network Manager | Open
R-010 | Security and System Documentation | Information | Outdated network and system documentation could lead to incorrect security decisions and increase recovery time during an incident. | Human error / configuration change | Documentation not maintained | Network diagram and project documentation | Medium – Integrity / Availability | 3 | 3 | 9 | Medium | Mitigate | Version-controlled documentation; review after significant changes; documented asset ownership | 2 | 3 | 6 | Medium | GRC Manager | Open

## Risk Criteria
Risk Level | Score | Treatment Guidance
Low | 1–4 | Accept and monitor
Medium | 5–9 | Consider additional controls
High | 10–14 | Treatment normally required
Critical | 15–25 | Immediate / priority treatment required

## Scoring Guide
Rating | Likelihood | Impact
1 | Rare | Insignificant
2 | Unlikely | Minor
3 | Possible | Moderate
4 | Likely | Major
5 | Almost Certain | Severe